## Instructions
Infrastructure Division Staff Instructions for Submittal Import Form
A/E Instructions (rows 3-12)
Submittal Tab | Instructions
Row 1, Column B | Input the TPWD project number
Column A - CSI Specification Section Code: | Input the 6 digit specification identifier associated with the category of submittal work to be performed
Column A format | XX XX XX
Column A example | 03 30 00; 11 68 16
Column B - CSI Specification Description: | Input description associated with specification code of work to be performed. Character limit: 100.
Column C - Category: | Use the "dropdown selection" within the template to select the category of work associated with the submittal submission.
Column D - Sub Section: | In coordination with TPWD DM, identify which submittals need to have TPWD concurrent review and utilize the "dropdown selection" to select "TPWD Review". If TPWD concurrent review not required for item, leave blank.
The submittal import form is a required deliverable from the A/E for all projects. Exhibit 4 of the specific Task Order will outline the design milestones for submission (at a minimum at 95% CD and 100% CD). A/E should upload this file into eB folder 5.4 in the Documents Module with the other required deliverables (CC: PM, KM, CPM). The A/E is also responsible for updating the form if there are addenda issued during the solicitation period that change the list of submittals.
File naming convention: DELIV_MilestoneCD_eBuilderSubmittalImportForm. Example: DELIV_100CD_eBuilderSubmittalImportForm
GC Instructions (rows 14-21)
Submittal Tab | Instructions
Column E-Critical Path: | Use the "dropdown selection" to select "Yes" or "No" to identify, if submittal submission is tied to the critical path of the project.
Column F - Date Due Submit For Review: | The General Contractor will input the date of submittal review.
Column F format | XX/XX/XX
Column F example | 05/01/20
Column G - Date Due Review Complete: | This field will automatically add 15 days to the date from Column "E" for review and approval. This will calculate the Date Due Review Complete.
Once completed the GC will upload this file through the Submittals Process in eBuilder. This process will be covered in the GC eBuilder orientation.
File naming convention: GC_eBSubmittalImportForm
Texas Parks and Wildlife Department maintains the information collected through this form. With few exceptions, you are entitled to be informed about the information we collect. Under Sections 552.021 and 552.023 of the Texas Government Code, you are also entitled to receive and review the information. Under Section 559.004, you are also entitled to have this information corrected.
PWD 1486-I0500 (08/2024) Texas Parks and Wildlife Department, 4200 Smith School Road, Austin, TX 78744, 800-792-1112, www.tpwd.texas.gov
End of sheet

## Eb Submittal Import Template
Project Number:
CSI Specification Section Code: | CSI Specification Description: Character limit 100 | Category: | Sub Section: | Critical Path?: | Date Due Submit For Review: | Date Due Review Complete
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
1900-01-14
Texas Parks and Wildlife Department maintains the information collected through this form. With few exceptions, you are entitled to be informed about the information we collect. Under Sections 552.021 and 552.023 of the Texas Government Code, you are also entitled to receive and review the information. Under Section 559.004, you are also entitled to have this information corrected.
PWD 1486-I0500 (08/2024) Texas Parks and Wildlife Department, 4200 Smith School Road, Austin, TX 78744, 800-792-1112, www.tpwd.texas.gov
Formulas:
Date Due Review Complete = [Date Due Submit For Review:]+15

## Sheet3 (hidden)
Title | Category | Description | Date Received From Sub | Date Returned | Date Delivered | Spec Section | Title | Category | Critical Path? | Date Due Submit For Review | Date Due Review Complete
[10 empty] | Valid Date | Valid Date
Certification
Mock Up
Operation / Maintenance Manual
Other
Product Data
Record Documents
Sample
Shop Drawing
Test Report
Warranties and Guarantees